## Product Backlog
User Story ID | User Story | Epic | Priority | Story Points | Sprint
US-01 | As a user, I want to sign up for an account in order to create a profile in the system. | EP-01 | Must | 5 | SP-1
US-02 | As a user, I want to login to the system in order to have secure access to my account. | EP-01 | Must | 5 | SP-1
US-03 | As a user, I want to file a lost item so that other users can locate the item and return it to its owner. | EP-02 | Must | 8 | SP-1
US-04 | As a user, I want to file a found item so that its owner is located and able to claim it back. | EP-02 | Must | 8 | SP-1
US-05 | As a user, I want to search for lost and found items in order to find a corresponding item. | EP-03 | Must | 8 | SP-1
US-06 | As a user, I want to filter lost and found items by relevant data in order to find corresponding records. | EP-03 | Should | 5 | SP-1
US-07 | As a user, I want to file a claim for a found item in order to prove that it belongs to me and get it back. | EP-04 | Must | 5 | SP-2
US-08 | As an administrator, I want to verify claims of items in order to let only real owners claim reported items. | EP-04 | Must | 5 | SP-2
US-09 | As a user, I want to get notifications about my reports and claims in order to be aware of their statuses. | EP-05 | Should | 2 | SP-2
US-10 | As an administrator, I want to update the status of reported items in order to keep the system up-to-date about items' status. | EP-05 | Should | 5 | SP-2
US-11 | As an administrator, I want to generate lost and found reports in order to monitor activities in the system. | EP-06 | Could | 5 | SP-2
|  |  |  | Total Story Points | 61

## Epics
Epic ID | Epic Name | Description | Linked User Stories
EP-01 | User Accounts Management | Registration and authentication services | US-01, US-02
EP-02 | Item Reporting | Service for reporting lost and found items | US-03, US-04
EP-03 | Item Search and Find | Services for searching and filtering items | US-05, US-06
EP-04 | Claims Management | Submission and Verification of Claims | US-07, US-08
EP-05 | Notifications and Status | Notifications and Management of Item Status | US-09, US-10
EP-06 | Administration and Reporting | Administrative Reporting and Monitoring | US-11

## Document Metadata
Document Title | Product Backlog
Document ID | DOC-04-PB
Version | 1.0
Project | Lost and Found Management System
Author | Kushal Shrestha
Stakeholder | Project Team and Instructor
Reviewed By | Suraj Kumar Gupta - Requirements & Design Analyst
Approved By | Professor Gaman Aryal - Instructor (pending approval)
Created On | 2026-08-24
Last Updated | 2026-08-24
Status | Under Review
Change Description | Initial product backlog spreadsheet based on the 11 user stories in the project report