## Sprint Tasks
User Story ID | Task / User Story | Epic | Priority | Story Points | Sprint | Final Report Status
US-07 | As a user, I want to file a claim for a found item in order to prove that it belongs to me and get it back. | EP-04 | Must | 5 | SP-2 | Done
US-08 | As an administrator, I want to verify claims of items in order to let only real owners claim reported items. | EP-04 | Must | 5 | SP-2 | Done
US-09 | As a user, I want to get notifications about my reports and claims in order to be aware of their statuses. | EP-05 | Should | 2 | SP-2 | Done
US-10 | As an administrator, I want to update the status of reported items in order to keep the system up-to-date about items' status. | EP-05 | Should | 5 | SP-2 | Done
US-11 | As an administrator, I want to generate lost and found reports in order to monitor activities in the system. | EP-06 | Could | 5 | SP-2 | Done
|  |  |  | Planned Story Points | 22
|  |  |  | Sprint Capacity | 45 | capacity units stated in report
|  |  |  | Remaining Capacity | 23

## Document Metadata
Document Title | Sprint 2 Planning & Execution
Document ID | DOC-05-SP2
Version | 1.0
Project | Lost and Found Management System
Author | Suraj Kumar Gupta
Stakeholder | Project Team and Instructor
Reviewed By | Manoj Karki - QA / Testing Analyst
Approved By | Professor Gaman Aryal - Instructor (pending approval)
Created On | 2026-08-24
Last Updated | 2026-08-24
Status | Under Review
Change Description | Initial Sprint 2 planning/execution spreadsheet based on the project report